18-DAY CAMPAIGN
TO END VIOLENCE AGAINST WOMEN

City Government of Cauayan, Isabela  •  November 25–December 12, 2026

Project S.U.N.S.H.I.N.E. for Safe, Inclusive and Technology-Responsive Communities

| COVERAGE | All LGU Cauayan Offices and 65 Barangays |
| --- | --- |
| CONVERGENCE PARTNERS | Province of Isabela, RGADC 2, NAPC, OPAPRU, PNP, DepEd, CSOs, POs, youth groups, and OGP partners |
| FOCUS AREAS | VAWC prevention and response, Technology-Facilitated Gender-Based Violence (TFGBV), cyber trafficking, online sexual exploitation, Safe Spaces, referral systems, survivor support, and community accountability |
| INTEGRATED PLATFORMS | Project S.U.N.S.H.I.N.E., iReport VAWC, Cauayan Safe Line, Cauayan CARES, and GERL/GAD KMS systems |

18-DAY ACTIVITY MATRIX

| DAY | DATE | LEAD OFFICE | PARTNER OFFICES | MAIN ACTIVITY |
| --- | --- | --- | --- | --- |
| 1 | Nov 25 | GAD Office &Office of the City Mayor | All City Offices, Barangays,Partners | Opening Program, Orange Campaign Kickoff, Orange Run, Policy Call to Action, Project S.U.N.S.H.I.N.E. public launch for VAWC, TFGBV, cyber trafficking, and online protection. |
| 2 | Nov 26 | City Legal Office | City Prosecutor's Office,PNP, DILG | Orientation on RA 9262, Safe Spaces Act, Anti-Trafficking, cyber-related VAWC and online crimes; legal referral pathways. |
| 3 | Nov 27 | CICTO /JCD Innovation Center | GAD Office, PNP, PLDT,Tech Partners | Digital Safety Day: demo of Project S.U.N.S.H.I.N.E., iReport VAWC, Safe Line, online reporting, cyber safety and digital evidence awareness. |
| 4 | Nov 28 | CSWDO | Health Office, PNP-WCPD,NGAs, CSOs | Survivor-centered care management, psychosocial first aid, women and children referral mapping. |
| 5 | Nov 29 | City Youth DevelopmentOffice / Kalinga KabataanProgram | DepEd, Sangguniang Kabataan,Wn Office, SangguniangPanlungsod, Youth Groups | Youth forum on online safety, consent, anti-bullying, anti-grooming, TFGBV and cyber trafficking prevention. |
| 6 | Nov 30 | PESO & CEDIPO | DOLE, OWWA, DTI,Private Sector | Women's economic empowerment, safe employment, anti-trafficking and cyber recruitment scam awareness. |
| 7 | Dec 1 | CHRMO & CODI | HR Units, DILG, CSOs | Safe workplace, anti-sexual harassment, internal reporting and protection mechanisms. |
| 8 | Dec 2 | CPDO / GAD KMS Team | IT Office, Planning Office,All Offices | Data-driven governance, sex-disaggregated data, monitoring dashboards, GERL and accountability tools. |
| 9 | Dec 3 | PDAO & OSCA | CSWDO, Health Office,PNP | Protection of women with disabilities and senior women; inclusive referral and access to support. |
| 10 | Dec 4 | City Population Office& MOVE | CSOs, Faith Groups,Youth Groups | Men as allies forum, healthy masculinity, shared responsibility, and prevention of VAWC and online abuse. |
| 11 | Dec 5 | City Agriculture Office &City Cooperative Office | DA, Cooperatives,Barangays | Rural women protection, livelihood, cooperative support, and community-based prevention. |
| 12 | Dec 6 | City Tourism / Culture Office /PIO / GAD Office | Local Artists, Media,Content Creators | Orange Exhibit and Orange Bubble: spoken poetry, declamation, spoken word, creative expression, advocacy through culture, IEC exhibit, public information campaign, and online awareness content. |
| 13 | Dec 7 | City Health Office | Hospitals, RHUs, NGOs,Mental Health Partners | Health response, mental health, reproductive health, medico-legal awareness, and support services for survivors. |
| 14 | Dec 8 | CDRRMO / Rescue 922 /Cauayan Safe Line | PNP, BFP, MDRRMO,All Response Teams | Emergency response simulation, hotline awareness, safety drill, and rapid coordination. |
| 15 | Dec 9 | Liga ng mga Barangay /Barangay VAW Desks | DILG, Barangays,BSWDO | Barangay action planning, desk strengthening, community watch, and referral readiness. |
| 16 | Dec 10 | PNP-WCPD / LCAT-JAWC /partner justice sector offices | City Prosecutor's Office,DILG, PNP, PAO | Case documentation, law enforcement coordination, protection procedures, and anti-online exploitation response. |
| 17 | Dec 11 | CSOs / POs / OGP Partners /Faith-based and community groups | All Community andDevelopment Partners | Multi-stakeholder dialogues, citizen participation, social accountability, survivor advocacy, and community partnership building. |
| 18 | Dec 12 | Culminating Activityled by LGU Cauayan | NAPC, OPAPRU, PCW,All Offices, All Partners | Awarding of all barangays and offices, recognition of partners, presentation of commitments, and ceremonial signing of Memorandum of Partnership with NAPC and OPAPRU. |

PARTICIPATION TARGETS

| MALE 975 | FEMALE 1215 | TOTAL 2190 |
| --- | --- | --- |